SAT TUTORING BUSINESS Master Business Plan The complete five-pillar blueprint for our SAT tutoring company A working document for Zakaria Bennis and Nabil Kafil Asrar Product • Marketing • Operations • Finance • People

Executive summary

This document is the master business plan for our subscription-based SAT tutoring platform targeting high school students and their parents across the United States. It synthesizes five supporting plans — Product Development, Marketing, Operations, Finance, and People and Culture — into a single strategic reference both founders use to align on direction.

The business is built on a tiered subscription model with four revenue streams, a web platform with diagnostics and animated lessons, a multi-city expansion structure, and a social media content engine that drives organic acquisition at low cost. Target: $50,000/month gross revenue within 12–18 months and a business valuation of $4M–$6M at year five.

| Target revenue (Y1) | Target revenue (Y3) | Business valuation (Y5) |
| --- | --- | --- |
| $50k/month | $84k/month | $4M–$6M |

How we work together

| Domain | Lead owner | Joint decision required |
| --- | --- | --- |
| Backend systems and product | Zakaria | Both review architecture decisions |
| Marketing and content | Nabil | Both approve brand standards |
| Operations and business systems | Joint | Both maintain SOPs |
| Brand voice and customer experience | Nabil | Both approve customer-facing copy |
| Tutoring sessions and curriculum | Joint — both equal | Both contribute equally |
| Tutor hiring | Joint — both interview | Both must agree on every hire |
| Pricing, finance, strategy | Joint | Both approve all major decisions |

Section 1 — The Market Opportunity

Market size and dynamics

The SAT preparation market is a multi-billion dollar segment of the broader private tutoring industry. Three structural forces make this a strong moment to enter:

- College admissions pressure is intensifying — acceptance rates at top universities have dropped to single digits, making test scores more differentiating, not less

- The digital SAT launched in 2024, creating a knowledge gap that existing preparation companies have not fully addressed

- The private tutoring market is projected to grow by $28.85 billion from 2025–2029 — driven by demand for personalized, outcome-focused education

- Online delivery removes the geographic constraint that limits traditional tutoring businesses — one platform can serve students in New York, Los Angeles, and Austin simultaneously

The competitive gap

Every competitor in this market has the same fundamental weakness: they offer either scale without personalization (Kaplan, Khan Academy) or personalization without scale (independent tutors). Nobody has built both simultaneously at our price point.

| Competitor | Strength | Price/month | Critical weakness |
| --- | --- | --- | --- |
| Kaplan / Princeton Review | Brand recognition | $150–$400 | Generic curriculum, no personalization, no live tutoring at this price |
| Khan Academy | Free, comprehensive | $0 | No accountability, no live support, no score guarantee |
| Independent $120/hr tutors | Personalization | $480–$960 | No platform, no tracking, inconsistent quality, high cost |
| Varsity Tutors / Wyzant | Marketplace scale | $80–$200 | No quality control, no curriculum, no parent reporting |
| Our business | All of the above | $40–$800 | None of their weaknesses — this is the gap we fill |

Our positioning

The only SAT platform that combines personalized diagnostics, animated concept lessons, and live tutoring — at a price parents actually accept. Students get a personalized path. Parents get weekly progress reports. Tutors get a platform that makes them better.

Section 2 — The Business Model

Four revenue streams

| Tier | Price | Revenue/unit/mo | Strategic purpose |
| --- | --- | --- | --- |
| Group class | $40/month | $40 per subscriber | Funnel entry — converts social followers to paying subscribers |
| Small group | $60/session per person | $1,200 per cohort (5 students, 4 sessions) | Highest revenue-per-hour tier — bridge between group and private |
| Private (weekly) | $135/session | $540/month per student | Premium positioning — weekly commitment creates retention |
| Elite package | $800/month | $800 per student (8 sessions) | Flagship product — parent-facing, outcome-guaranteed, highest LTV |

Revenue model economics

| Metric | Target (Month 12) | Target (Year 3) |
| --- | --- | --- |
| Gross margin | 78–82% | 80–85% |
| Monthly churn rate | <5% | <3% |
| Trial to paid conversion | >60% | >70% |
| Average revenue per user | $85/month blended | $110/month blended |
| Customer acquisition cost | <$40 (organic dominant) | <$25 |
| LTV:CAC ratio | >12:1 | >20:1 |

The $40 minimum access model

There is no free tier. Every platform feature requires a minimum $40/month subscription. The top-of-funnel delivers value without platform access:

- Free diagnostic landing page — no account required, email captured before results shown

- YouTube sample lessons — 10–15 full concept lessons publicly available as quality proof

- 7-day free trial — card required, full access, auto-converts on day 8

- Instagram and TikTok content — educational value drives follows, follows drive trial signups

Section 3 — The Product Summary

Full details in the Product Development Plan. Summary here for cross-reference. Zakaria leads on backend architecture and developer management; Nabil leads on UI/UX and brand visuals; both founders contribute equally to curriculum content.

Platform architecture summary

| Feature | What it does | Why it matters competitively |
| --- | --- | --- |
| Diagnostic engine | 44-question adaptive assessment, generates personalized weakness map and study path | No competitor offers this level of diagnostic specificity at $40/month |
| Curriculum graph | Branched concept network, 70–90 nodes, mastery-unlocked progression | Gives students a visible map of their journey |
| Manim animations | Professional math animations rendered free on Google Colab | Studio-quality explanations at zero marginal cost |
| Tutor dashboard | Real-time weakness heatmap, session prep brief, one-click parent report | Tutors arrive prepared — session quality is visibly higher |
| Parent dashboard | Weekly automated digest, score trajectory, direct tutor messaging | Parents feel in control — primary purchase driver for Elite |

Build timeline and cost

| Phase | Deliverable | Without AI | With AI | Timeline |
| --- | --- | --- | --- | --- |
| Phase 1 | MVP — paywall + diagnostic + core lessons | $5k–$8k | $2.5k–$4k | 4–6 wks |
| Phase 2 | Full curriculum graph + animations | $8k–$12k | $4k–$6k | 6–8 wks |
| Phase 3 | Tutor and parent dashboards | $5k–$8k | $3k–$5k | 5–7 wks |
| Phase 4 | Polish + QA + launch readiness | $3k–$5k | $1.5k–$3k | 3–4 wks |
| Content | 70–90 animated lessons + 500+ questions | $10k–$20k | $0 (AI pipeline) | Ongoing |
| TOTAL | Full platform | $31k–$53k | $11k–$18k | ~7–8 months |

Section 4 — Marketing Summary

Full details in the Marketing Plan. Nabil leads marketing strategy and content production; Zakaria supports with analytics and attribution tracking; both founders review brand standards.

Channel strategy

| Channel | Audience | Goal | Cost | Target KPI |
| --- | --- | --- | --- | --- |
| TikTok | Students 15–18 | Discovery | $0 | Daily posts, 8%+ save rate |
| Instagram | Parents 35–55 | Trust + conversion | $0 organic / paid | Trial signups from bio link |
| YouTube | Both | Deep trust + free tier | $0 | 2–3 videos/week, sub growth |
| SEO/Blog | Parents searching | Organic compound | $0 (AI writes) | 50 articles, top 3 rankings |
| Email | Both | Nurture + retention | $0–$20/mo | 35%+ open rate, 60% trial conversion |
| Reddit/Discord | Both | Community trust | $0 | 200+ genuine answers/month |
| Paid ads | Parents (Meta) | Scale proven funnel | Month 3+: $600–$3,000/mo | CAC below $40 |

The content machine — one session, six channels

Film one 60-second SAT concept explanation. It becomes: a YouTube full lesson (15 min with Manim animation), a TikTok clip, an Instagram Reel, a blog section, a platform lesson, and an email newsletter tip. One filming session produces a week of content across all channels.

90-day launch targets

| Month | Month 1 | Month 2 | Month 3 |
| --- | --- | --- | --- |
| Email subscribers | 50–100 | 200–300 | 500+ |
| Trial signups | 10–20 | 40–60 | 120–160 |
| Paying subscribers | 5–10 | 25–40 | 100–150 |
| Monthly revenue | $1,000–$2,000 | $4,000–$8,000 | $12,000–$20,000 |
| TikTok followers | 200–500 | 1,500–3,000 | 4,000–7,000 |

Section 5 — Operations Summary

Full details in the Operations Plan. Zakaria leads on backend systems and SOPs; Nabil leads on customer voice and tutor experience; both founders interview and approve every tutor hire.

The five operational pillars

| Student journey | Every interaction from lead capture to post-test celebration is automated and personalized. 7-stage pipeline from pre-enrollment to offboarding. |
| --- | --- |
| Session ops | Standardized 60-minute session structure across all tutors. Automated booking, reminders, notes, and follow-up. Both founders defined the structure. |
| Tutor management | Hiring pipeline with both founders interviewing every candidate. 5-module certification required before first session. Bi-weekly payment via Stripe Connect. |
| Customer support | AI-powered chatbot handles 70% of tickets. 4-hour response SLA. Escalation protocol with three levels. |
| Business systems | 30 SOPs documented in Notion within 90 days. Weekly automated operations report. Scaling triggers defined at 100, 200, 400, and 600 subscribers. |

Scaling triggers

| Subscriber count | What breaks | The hire |
| --- | --- | --- |
| 100 subscribers | Support ticket volume exceeds founder bandwidth | Part-time admin at $2,000/month |
| 200 subscribers | Tutor capacity at 80% — waitlist forming | Third tutor at $50/hr (variable) |
| 400 subscribers | Admin overwhelmed — operations becomes bottleneck | Admin upgraded to full-time |
| 600 subscribers | Founders cannot focus on growth | Ops manager at $50,000/year |

Section 6 — Finance Summary

Full details in the Finance Plan. Zakaria leads on financial management and CPA relationship; both founders have full visibility into every account; major financial decisions require both founders' agreement.

Revenue projections — 5-year summary

| Metric | M6 | M12 | Y2 | Y3 | Y4 | Y5 |
| --- | --- | --- | --- | --- | --- | --- |
| Gross revenue/mo | $29,800 | $51,680 | $69,200 | $84,000 | $99,400 | $115,200 |
| Total overhead/mo | $3,200 | $5,400 | $8,200 | $10,500 | $14,000 | $17,500 |
| Net profit/mo | $26,600 | $46,280 | $61,000 | $73,500 | $85,400 | $97,700 |

Tax and legal structure

- Phase 1 (months 1–12): Multi-member Texas LLC — $300 formation fee — 50/50 ownership

- Phase 2 (when net profit exceeds $60k/year): S-Corp election — saves $13,000–$22,000/year per founder

- Phase 3 (year 2–3): Holding company structure — parent LLC owns all city subsidiaries

- Quarterly estimated taxes: 28–30% of all revenue set aside immediately

- CPA engagement: year 1 — $2,000–$4,000/year retainer — required for S-Corp election

Founder draw policy summary

| MRR milestone | Each founder | Combined | Reserve |
| --- | --- | --- | --- |
| Months 1–3 | $0 | $0 | All revenue stays in business |
| MRR > $10,000 | $2,000/mo | $4,000/mo | 1 month of expenses |
| MRR > $20,000 | $4,000/mo | $8,000/mo | 2 months of expenses |
| MRR > $50,000 | $8,000/mo | $16,000/mo | 3 months of expenses |

Section 7 — People and Culture Summary

Full details in the People and Culture Plan. Both founders contribute equally to all hiring, training, and culture decisions.

Cofounder agreement essentials

- Equity: 50/50 split — 4-year vest with 1-year cliff — monthly vesting after month 12

- Roles defined per the role split table above — clear lanes, joint decisions on lane-crossing topics

- Compensation: equal draws at every milestone, never asymmetric

- Exit provisions: voluntary exit at vested equity fair market value over 24 months

- Friendship clause: if business ever threatens the friendship, friendship comes first — stated explicitly before signing

The three non-negotiable values

| Value | What it requires | What it prohibits |
| --- | --- | --- |
| Results over effort | Every metric is an outcome metric. Tutors evaluated on score improvements. | Celebrating busy-work. Spinning slow progress as success. |
| Respect for student time | Tutors arrive prepared. Lessons are efficient. Communication is brief and actionable. | Underprepared sessions. Padding lesson time. |
| Honesty | We tell students and parents the truth about progress. | Inflated score predictions to win a sale. Hiding slow progress. |

Team structure summary

| Phase | Team size | Monthly people cost | Key milestone |
| --- | --- | --- | --- |
| Months 1–3 | 2 (founders) | $0 draws | First $10k MRR |
| Months 4–6 | 3 (+ admin) | $2,000 draws each + $2,000 admin = $6,000 | First $20k MRR |
| Months 6–9 | 4 (+ third tutor) | Variable tutor cost added | First $35k MRR |
| Year 2 | 6–8 | Founders + admin + tutors + ops manager | First subsidiary launch |
| Year 3+ | 15–25 | City lead tutors + regional teams | 4-city operation |

Section 8 — Multi-City Expansion Model

The single-city model is validated first. Then the playbook is documented. Then it is replicated city by city — each subsidiary appearing local while profits flow to the parent. By year 5 we are running an education company, not a single tutoring service.

Expansion roadmap

| Timeline | Action | Trigger | Expected impact |
| --- | --- | --- | --- |
| Months 1–12 | Perfect the Austin/Online core model | First $50k/mo month | Proven playbook — replication-ready |
| Month 15–18 | Launch NYC subsidiary | Core model profitable and systematized | +$20k–$35k/mo at 6-month mark |
| Month 20–24 | Launch LA subsidiary | NYC subsidiary profitable | +$20k–$30k/mo at 6-month mark |
| Year 3 | Launch Chicago subsidiary | Two subsidiaries profitable | +$15k–$25k/mo at 6-month mark |
| Year 4 | Launch Houston or DC | Three subsidiaries profitable | Total holdco revenue $150k–$180k/mo |

What makes each subsidiary local

- Separate Instagram and TikTok account with local branding

- Local lead tutor who is the face of the brand in that market

- City-specific SEO pages targeting local search

- Local pricing awareness — premium markets support higher Elite and private tier pricing

- Local school counselor relationships — the B2B acquisition channel that works market-by-market

- Same curriculum, same platform, same standards — only the local face and marketing change

Section 9 — Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Cofounder conflict or exit | Medium | Very High | Cofounder agreement with vesting, monthly check-ins, friendship clause |
| Instagram algorithm change | High | Medium | Multi-platform presence — no single-channel dependency |
| College Board changes SAT format | Medium | High | Post-SAT analysis content strategy — rapid curriculum update via AI within 2 weeks |
| Tutor quality incident | Medium | High | 5-module certification, shadow sessions, monthly QA reviews, guarantee honored |
| Platform security breach | Low | Very High | Database security policies, auth, deletion workflow, E&O insurance, incident response plan |
| Founder burnout | Medium | Very High | Scaling triggers add resources before burnout, monthly partnership check-ins |
| Well-funded competitor enters | Medium | Medium | Brand moat (social, results), community, price positioning |
| TikTok ban in the US | Low–Medium | Medium | Instagram and YouTube as primary channels — TikTok is distribution not foundation |
| Trial conversion below 60% | Medium | High | A/B test landing page and onboarding using Posthog — iterate weekly |
| Skill gaps in business basics | High | High | Both founders flag gaps openly, hire CPA and lawyer early, learn continuously |

Section 10 — Milestone Roadmap — 5 Years in 20 Quarters

| Period | Revenue target | Key milestone | Product | People |
| --- | --- | --- | --- | --- |
| Q1 Y1 | $2k–$5k/mo | Platform MVP live, first 50 subscribers | Phase 1 build underway | 2 founders |
| Q2 Y1 | $8k–$15k/mo | 150 subscribers, first Elite students | Phase 2 curriculum graph | 2 founders |
| Q3 Y1 | $18k–$28k/mo | 300 subscribers, first score wins posted | Phase 3 dashboards | Admin hired |
| Q4 Y1 | $35k–$50k/mo | 500 subscribers, $50k/mo target | Phase 4 polish complete | Third tutor hired |
| Q1 Y2 | $50k–$60k/mo | First $50k+ month, NYC planned | Annual subscriptions live | Ops manager hired |
| Q2 Y2 | $58k–$70k/mo | NYC subsidiary launched | NYC platform branded | NYC lead tutor |
| Q3 Y2 | $68k–$80k/mo | NYC profitable | Digital products live | NYC full team |
| Q4 Y2 | $75k–$90k/mo | LA planned, $1M ARR milestone | School licensing tier | LA lead tutor search |
| Q1 Y3 | $80k–$95k/mo | LA launched | City-specific landing pages | LA team hired |
| Q2 Y3 | $85k–$100k/mo | 3-city operation stable | Curriculum refresh | Regional ops structure |
| Q3 Y3 | $90k–$105k/mo | Chicago planned | Curriculum refresh post-SAT | City lead onboarding |
| Q4 Y3 | $95k–$110k/mo | Chicago launched | School district deal target | 4-city ops team |
| Q1 Y4 | $100k–$120k/mo | Strategic review | CEO hire considered | Ops manager runs day-to-day |
| Q2 Y4 | $105k–$125k/mo | Possible 5th city scoped | Platform v2 evaluation | Founders step back from daily ops |
| Q3 Y4 | $108k–$128k/mo | Sale or hold strategic decision | Sale or hold analysis | Founders = strategists |
| Q4 Y4 | $110k–$130k/mo | Exit or hold decision finalized | Audited financials prepared | Succession plan if exiting |
| Q1 Y5 | $112k–$135k/mo | Business fully systematized | Data room prepared for sale | Leadership team complete |
| Q2 Y5 | $115k–$138k/mo | Acquisition conversations or CEO hired | All SOPs documented | Founders free |
| Q3 Y5 | $115k–$140k/mo | Transaction completed if exiting | Post-exit plan active | Business asset realized |
| Q4 Y5 | $115k–$140k/mo | 5-year vision complete | Legacy and next chapter | What is next together? |

Closing — The Five Documents That Make This Real

This master plan synthesizes our complete business strategy across product, marketing, operations, finance, and people. Each section above is supported by a dedicated document with the granular detail we need to execute. Both founders should review this master plan together monthly and update it as the business evolves.

| Document | Lead owner | What it gives us |
| --- | --- | --- |
| Product Development Plan | Zakaria leads, both review | The exact step-by-step build plan with phases, costs, and tools |
| Marketing Plan | Nabil leads, both review | The full acquisition, conversion, and retention strategy |
| Operations Plan | Zakaria leads, both review | Every operational process automated, documented, and scalable |
| Finance Plan | Zakaria leads, both review | Revenue model, tax strategy, founder draw policy, exit scenarios |
| People and Culture Plan | Joint — both equal | Cofounder agreement, hiring pipeline, training curriculum, culture |
| This Master Plan | Joint — both equal | The synthesis we use to align on strategic direction |

Every section of every document is a starting point for our discussion — not a final answer. Both founders revise these together as we learn what works and what does not. The plans evolve. The partnership and the values do not.

We are equal partners building something neither of us could build alone. The complementary strengths, the explicit role split, and the willingness to learn together are what make this work. The math is in our favor. The execution is in our hands.